VOLUME 2

SECTION 3

SPECIAL CONDITIONS FOR EUROPEAN UNION EXTERNAL ACTIONS

# CONTENTS

# These conditions amplify and supplement the general conditions governing the contract. Unless the special conditions provide otherwise, the general conditions remain fully applicable. The numbering of the articles of the special conditions is not consecutive but follows the numbering of the general conditions. Exceptionally, and with the approval of the competent European Commission departments, other clauses can be indicated to cover particular situations.

# Contract value

# The contracting authority hereby agrees to pay to the contractor, in consideration of the execution and completion of the works and remedying of defects therein, the amount of the contract value mentioned in article 2 of the Main Conditions or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the contract. VAT will be paid in compliance with the binding regulations, national law and international agreements concerning the execution of the project.

# The amount of the contract value mentioned in article 2 of the Main Conditions shall be composed of:

- Contract price (excluding VAT/other taxes) [EUR]

-	VAT and other taxes [EUR]

# Order of precedence of contract documents

The following documents shall be deemed to form and be read and construed as part of this contract, in the following order of precedence:

- The main conditions

- the special conditions,

- the general conditions,

- [Only for contracts financed by post 2021 instruments (NDICI, IPA III, etc. [only where the PRAG Procedural rules are chosen in the special conditions]): applicable only if the contract is a transnational contract: the PRAG Procedural rules on conciliation and arbitration.]

- the bill of quantities (after arithmetical corrections) and detailed breakdown of prices

- the technical and/or performance specifications,

- the design documentation (drawings),

- the tender

- any other documents forming part of the contract.

The various documents making up the contract shall be deemed to be mutually explanatory; in cases of ambiguity or divergence, they shall prevail in the order in which they appear above. Addenda shall have the order of precedence of the document they are amending.

Article 2	Language of the contract

2.1	The language used shall be English.

Article 4	Communication

4.1	Communication details

4.4	Communication via electronic exchange system (EES)

4.5 & 4.6 	Mail or email communication

If communications through the Portal have not been activated or a certain type of communication is not yet supported by the Portal, communications will be sent via email, or, exceptionally, on paper, via mail services, to the following addresses, until communications via the Portal are activated.

For the purpose of this contract, mail or email communications must be sent to the following addresses:

Contracting authority:

Municipality of Gevgelija, Republic of North Macedonia

4, Dimitar Vlahov str., Gevgelija

Email: regreen.pp2@gmail.com

Contractor (or leader in the case of a joint tender):

[Full name]

[Function]

[Company name]

[Full official address]

Email: [complete]

Article 5	Supervisor and supervisor’s representative

5.2	The power of the Supervisor and its representative is in compliance with Macedonian legislation. The Construction Supervisor will be assigned by the contracting authority with separate service contract. The purpose of the service contract is the provision of Independent Construction Supervisor for the implementation of the construction works required by the project in compliance with Macedonian legislation for Construction works and all relevant Regulations.

5.3	Any approval, inspection, certificate, examination, instruction, proposal, request, test or other similar action of the Supervisor shall not relieve the Contractor of any of his duties and responsibilities under this Contract, including responsibilities for any of his mistakes, faults or discrepancies.

The Contractor must ensure that the Supervisor has free access to the construction (s) and all the documentation relevant to the implementation of the current contract and the works herein. The Supervisor shall have access to all materials or items to be installed on the sites before they are actually fixed in place.

5.4	Instructions and/or orders issued by the Supervisor shall be by way of administrative orders. All administrative order by the Supervisor shall be issued in three copies, one for the Supervisor, one for the Contracting Authority and one for the Contractor.

Article 8	Documents to be provided

8.1	The supervisor shall provide to the contractor electronic version of the drawings prepared for the implementation of the tasks in dwg and pdf format.

The contractor shall give prompt notice to the supervisor, about any omission, fault, or other defect in the design the he discovers before executing the works. However, this situation shall not relieve the contractor of any of his obligation under the contract.

Article 9	Access to the site

9.1	The contractor is reminded that there is a head of delegation of the European Unionin the state of the contracting authority. The contractor is obliged to give the head of delegation free access to its sites, factories, workshops, etc., and generally assist the head of delegation, like the project Supervisor, in the performance of his duties. The same provisions also apply to the appointed representatives of the head of delegation.

All correspondence between the contractor and the contracting authority or project supervisor must be copied, for information, to the head of delegation of the European Commission at the following official address:

Contracting authority:

Municipality of Gevgelija, Republic of North Macedonia

4, Dimitar Vlahov str., Gevgelija

Article 12	General obligations

12.9	The visibility measures must comply with the rules laid down in the Communication and Visibility Manual for EU External Actions published by the European Commission: https://international-partnerships.ec.europa.eu/knowledge-hub/communicating-and-raising-eu-visibility_en and the latest version of the Project Implementation Manual (PIM) of the Interreg (VI-A) IPA CBC Bulgaria - North Macedonia 2021-2027 Programme published on the Programme’s website: https://ipa-bgmk.mrrb.bg/index.php/en/node/221.

Article 15	Performance guarantee

15.1	The amount of the performance guarantee will be 5 % of the amount of the contract and any addenda thereto.

Article 16	Liabilities and insurance

16.1 a)	By way of derogation from Article 16.1, a) paragraph 2, of the general conditions, compensation for damage to the works resulting from the contractor's liability in respect of the contracting authority is capped at an amount equal to the contract value.

16.1 b)	By way of derogation from Article 16.1, b), paragraph 2, of the general conditions, compensation for damage resulting from the contractor's liability in respect of the contracting authority is capped at an amount equal to the contract value.

Article 17	Programme of implementation of tasks

17.1	The contractor shall provide the supervisor with a simplified programme of implementation of the tasks. This programme shall include at least the order and time limits in which the contractor proposes to carry out the works, and shall be based on the tranches foreseen in Article 49.1 of the special conditions.

17.2. 	The supervisor shall return this document to the contractor with any relevant remarks within 10 days of receipt, save where the supervisor, within those 10 days, notifies the contractor of its wish for a meeting in order to discuss the documents submitted.

Article 19	Contractor’s drawings and execution studies

19.1	The manuals and as-built drawings shall be supplied in paper and electronic copy to the supervisor.

19.7	The language of the manuals and drawings can be in Macedonian, different than the language of the contract.

Article 20	Sufficiency of tender prices

As per General Conditions.

Article 21	Exceptional risks

21.4	The following weather conditions, confirmed by the nearest official meteorological station (e.g. the National Hydro-meteorological Service of North Macedonia), shall be considered exceptional and may justify an extension of the period of implementation under Article 35 of the General Conditions:

- Heavy rainfall exceeding 60 mm in a 24-hour period, or cumulative rainfall causing flooding or rendering the site inaccessible or unsafe;

- Snowfall or snow accumulation exceeding 10 cm within 24 hours, or conditions that prevent safe access to or within the site;

-	Sub-zero temperatures: when daily average temperatures remain below -2°C for three (3) or more consecutive days, affecting external construction activities (e.g. concrete works, facade works, roofing);

-	Heat waves: when daily maximum temperatures exceed 40°C for three (3) or more consecutive days, affecting the ability of workers to safely perform outdoor manual tasks;

-	Strong winds: sustained winds exceeding 60 km/h, which prevent safe operation of cranes, scaffolding, lifting equipment e.tc.

Article 24	Interference with traffic

24.1	As per General Conditions.

24.2	As per General Conditions.

Article 27	Demolished materials

27.2	Demolition materials are the property of the Contracting Authority in accordance to Technical specification and work description for this contract.

27.4	The Contractor is obligated to remove demolition material.

Article 29	Temporary works

29.2	As per General Conditions.

Article 30	Soil studies

30.1	As per General Conditions.

Article 32	Patents and licenses

32.1	As per General Conditions.

Article 34	Period of implementation of tasks

# 34.1	The period of implementation of tasks is 12 (twelve) months, and not later than 25 of August 2027

Article 36	Delays in the implementation of tasks

36.1      The rate of liquidated damages for delays in the completion of works shall be 0.1% of the contract price for every day or part thereof which elapses between the end of the period of implementation of tasks and the actual date of completion, up to a maximum amount of 10 % of the contract price or, if the contract is subdivided into phases, 10 % of the price of the phase concerned.

Article 39	Work register

39.1	The Contractor shall maintain a comprehensive record of the construction process, including an archive of all documentation relevant to the implementation of the works.

39.2	To contractor shall keep record of the following documents:

- Construction log-book;

- Construction/building book;

- Time situation(s) - Invoice(s).

Article 40	Origin and quality of works and materials

40.1      All goods purchased and materials under the contract may originate in any country.

## For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or the applicable international agreement.

When importing goods, any change in the specified origin must be pointed out to the project supervisor and approved by him.

40.2	The works and the objects, appliances, equipment or materials used in their construction must comply with:

(*)	the following specifications Technical Specification Volume 3 of TD

(*)	the requirements of detailed design (Volume 5)

40.3	The preliminary technical acceptance will be conducted according the national legislation and the conditions governing its implementation. The acceptance will be confirmed by the Supervisor.

Article 41	Inspection and testing

41.3 	The contractor shall give notice to the supervisor when any work is ready before it is covered up. The supervisor shall either carry out the examination inspection and testing without in a reasonable delay or promptly gift notice to the contractor that he does not intend to do so. In the case the contractor fails to give notice, upon supervisor requests, he shall uncover the work reinstating and making good to the supervisor satisfactions all activity will be performed at the contractor's cost, regardless of previous positive test results.

41.8 	Inspection and testing shall be performed in accordance with the requirements of the applicable technical regulation and local legislation. All materials and equipment used are subject to inspection by the supervisor and/or his substitutes on arrival to the site.

Article 43	Ownership of plant and materials

43.2	Equipment and materials intended for incorporation in the permanent works, but not yet incorporated in the permanent works and for which any interim payment has been made by the Contracting Authority, shall be vested in the Contracting Authority.

Article 44:	General principles for payments

44.1	Payments shall be made in MKD.

44.3     By derogation, pre-financing payment to the contractor for the lump-sum advance shall be made within 30 days. Other pre-financing payments to the contractor shall be made within 90 days. Interim payments to the contractor of the amounts due under each of the interim payment certificates approved by the supervisor shall be made within 90 days, and the final payment to the contractor of the amounts due after the final statement of account issued by the supervisor shall be made within 90 days.

Article 46	Pre-financing

46.1      The only pre-financing granted to the contractor, is the lump sum advance referred to in Article 46.1(a).

46.2	The lump sum advance referred to in Article 46.1(a) shall be 10% of the original contract price

46.3(c)  By derogation from Article 46.3(c) of the general conditions no pre-financing guarantee is required.

46.8	Repayment of the pre-financing shall take the form of deductions based on monthly claims.

- The flat-rate pre-financing (maximum of 10 %) shall be repaid by means of deductions from instalments and, if necessary, the balance due to the contractor. This repayment shall begin with the first instalment and be completed, at the very latest, by the time 80 % of the amount of the contract has been paid.

Repayment shall be made in the same currency as the pre-financing.

The amount to be deducted from each instalment shall be calculated using the following formula:

where:

R = the amount to be repaid

Va = the total amount of pre-financing

Vt = the initial contract amount

D = the amount of the instalment.

The result is rounded up to two decimal places.

- The pre-financing for plant, machinery and tools — and the pre-financing for other major prior outlays (20 % maximum) — shall be repaid by means of deductions from instalments and, if necessary, the balance due to the contractor. Repayment shall begin with the first instalment and end, at the very latest, by the time 90 % of the amount of the contract has been paid.

The amount to be deducted from each instalment shall be calculated using the following formula:

where:

R = the amount to be repaid

Va = the total amount of pre-financing

Vt = the initial contract amount

D = the amount of the instalment.

Article 47	Retention monies

47.1	The sum retained to guarantee implementation of the contractor’s obligations during the defects liability period is 10 % of the contract price. By derogation to Article 47.1 of the general conditions, that money is not retained from interim payments. The tranches laid down in Article 49.1 of these special conditions are determined so that the retention sum amounts to 10% of the contract price at the moment of the certificate of provisional acceptance.

47.2	By derogation to Article 47.2 of the general conditions, the retention sums cannot be substituted by a retention guarantee.

Article 48	Price revision

48.1	    Prices are fixed and shall not be revised.

Article 49	Measurement

49.1	(*) This is a unit-price contract.

All items in the Bill of Quantities are based on unit price, so this is unit-price contract.

Under the conditions imposed by the Special Conditions and General Conditions, the amounts due shall be calculated through the following tranches, expressed as percentage of the contract price:

|  | Percentage | Nature | Timing |
| --- | --- | --- | --- |
| 1. | 10% | Lump-sum advance of Article 46.1(a) | After conclusion of the contract |
| 2. | 20% | Interim payment of Article 50 | After completion of 40% of the firm quantities for which the Contractor submitted its all-in price. |
| 4. | 20% | Interim payment of Article 50 | After completion of 60% of the firm quantities for which the Contractor submitted its all-in price. |
| 5 | 25% | Interim payment of Article 50 | After completion of 80% of the firm quantities for which the Contractor submitted its all-in price. |
| <last> | 25% | Final/Balance payment /Retention money of Article 47 | Within 45 days of the issuing of the signed Final statement of account (according to applicable national legislation for construction works) |

Article 50	Interim payments

50.1	The interim payments will be paid as determined in Article 49.1 of these special conditions.

Article 51	Final statement of account

51.1	The contractor shall, submit to the supervisor a draft final statement of account when it applies for the final acceptance certificate. In order to enable the supervisor to prepare the final statement of account, the draft final statement of account is submitted with supporting documents showing in detail the value of the work done in accordance with the contract and all further sums which the contractor considers to be due to it under the contract.

51.2	Within 30 days from issuing the final acceptance certificate referred to in Article 62, the supervisor shall prepare and signed the final statement of account.

Article 59	Partial acceptance

59.3	The defects liability period provided for in Article 61 shall run from the date of provisional acceptance certificate.

Article 60	Provisional acceptance

60.1	In complement to article 60.1 of the General Conditions provisional acceptance should follow the respective procedure laid down in the national legislation.

Article 61	Defects liability

61.1	The defects liability period is defined as the period commencing on the date of provisional acceptance, during which the contractor is required to make good any defect in, or damage to, any part of the work which may appear or occur during this period as notify by the supervisor or the contracting authority. The rights and obligations of the parties with regard to this defects liability period are laid down in Article 61 of the general conditions.

Article 68	Dispute settlement

68.4	Any dispute arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of Court of law in Gevgelija in accordance with the national legislation of the state of the Contracting Authority.

Article 72	Data protection

For the purpose of Article 72 of the general conditions, for the part of the data transferred by the contracting authority to the European Commission:

(a) the controller for the processing of personal data carried out within the Commission is the head of contracts and finance unit R4 of DG Neighbourhood and Enlargement Negotiations

- the privacy statement is available at http://ec.europa.eu/europeaid/prag/annexes.do?chapterTitleCode=A.

1. Processing of personal data related to the implementation of the contract by the contracting authority takes place in accordance with the national legislation of the state of the contracting authority and with the provisions of the respective financing agreement.

2. To the extent that the contract covers an action financed by the European Union, the Contracting Authority may share communications related to the implementation of the contract, with the European Commission. These exchanges shall be made to the Commission, solely for the purpose of allowing the latter to exercise its rights and obligations under the applicable legislative framework and under the financing agreement with the Partner country – contracting authority. The exchanges may involve transfers of personal data (such as names, contact details, signatures and CVs) of natural persons involved in the implementation of the contract (such as contractors, staff, experts, trainees, subcontractors, insurers, guarantors, auditors and legal counsel). In cases where the contractor is processing personal data in the context of the implementation of the contract, he/she shall accordingly inform the data subjects of the possible transmission of their data to the Commission. When personal data is transmitted to the Commission, the latter processes them in accordance with Regulation (EU) 2018/1725 of the European Parliament and of the Council of 23 October 2018 on the protection of natural persons with regard to the processing of personal data by the Union institutions, bodies, offices and agencies and on the free movement of such data, and repealing Regulation (EC) No 45/2001 and Decision No 1247/2002/EC and as detailed in the specific privacy statement published at ePRAG.

* * *

See internal provision in the Companion Chapter 9.

OJ L 205 of 21.11.2018, p. 39